## LLTC Readiness
LLTC Readiness
EPIC | User Story ID | Description | Release | Sprint | Status | Version | Remarks | No. of Test case | No. of Test step
EP-001 | US-001 | User Authentication | R1.0 | 1 | In progress | v.1.0 |  | 6 | 19
EP-002 | US-002 | Dashboard/Home | R1.0 | 1 | In progress | v.1.0 |  | 11 | 34
EP-003 | US-003 | Withdraw Earned Wage | R1.0 | 1 | In progress | v.1.0 |  | 3 | 17
EP-003 | US-004 | Transaction Confirmation & Slip | R1.0 | 1 | In progress | v.1.0 |  | 3 | 27
EP-004 | US-005 | Transaction History | R1.0 | 1 | In progress | v.1.0 |  | 5 | 28
EP-005 | US-006 | Session Management | R1.0 | 1 | In progress | v.1.0 |  | 3 | 14
Figma:
Flow:

## Test Execution Plan
Test Execution Plan
Date | TOTAL PLANNED | TOTAL TESTED | TARGET @CHECKPOINT 1 (1 PM) | TARGET @CHECKPOINT 2 (4 PM) | SIT EXECUTION DASHBOARD
[5 empty] | TC_US-001 (xx) |  |  |  |  | TC_US-002 (xx) |  |  |  |  | TC_US-003 (xx) |  |  |  |  | TC_US-004 (xx) |  |  |  |  | TC_US-005 (xx) |  |  |  |  | TC_US-006 (xx)
[5 empty] | Planned | Tested | Pass | Failed | Pending | Planned | Tested | Pass | Failed | Pending | Planned | Tested | Pass | Failed | Pending | Planned | Tested | Pass | Failed | Pending | Planned | Tested | Pass | Failed | Pending | Planned | Tested | Pass | Failed | Pending
2025-05-26
2025-05-27
2025-05-28
2025-05-29
2025-05-30

## Test Execution Dashboard
All Test cases
Summary | Tested | Not Start | Pending | Pass | Failed | Not Applicable | Test Rate | Pass Rate | Failed Rate
TC_US-001 | 0 | 6 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-002 | 0 | 11 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-003 | 0 | 3 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-004 | 0 | 5 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-005 | 0 | 3 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-006 | 0 | 31 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Total | 0 | 59 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Positive Test cases
Summary | Tested | Not Start | Pending | Pass | Failed | Not Applicable | Test Rate | Pass Rate | Failed Rate
TC_US-001 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-002 | 0 | 11 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-003 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-004 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-005 | 0 | 5 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-006 | 0 | 3 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Total | 0 | 25 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Negative Test cases
Summary | Tested | Not Start | Pending | Pass | Failed | Not Applicable | Test Rate | Pass Rate | Failed Rate
TC_US-001 | 0 | 4 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-002 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-003 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-004 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-005 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-006 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Total | 0 | 6 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Negative (Exception) Test cases
Summary | Tested | Not Start | Pending | Pass | Failed | Not Applicable | Test Rate | Pass Rate | Failed Rate
TC_US-001 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-002 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-003 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-004 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-005 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TC_US-006 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%

## TC_US-001
TC No. | US ID | P/N/NE | Priority | Test Case Description | Prerequisite | Ts No | Test steps Description | Expected Result | API Tesing | [5 empty] | Remarks
[9 empty] | Executor | Plan date | Ts Result | TC Result | Test Date | Defect ID
TC_EP-001_US-001_0001 | US-001 | P | High | Verify login with valid phone number | User has a registered account with a valid phone number | 1 | Open the Salary Hero app | App launches successfully and login screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Enter a valid phone number in the phone number field | Phone number is accepted and displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Click on the Continue/Next button | OTP screen is displayed and OTP is sent to the provided phone number | QA Team | 2025-05-23 | Not Start
TC_EP-001_US-001_0002 | US-001 | N | High | Verify login with invalid phone number | N/A | 1 | Open the Salary Hero app | App launches successfully and login screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Enter an invalid phone number (e.g., wrong format, non-existent) | Phone number is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Click on the Continue/Next button | Error message is displayed indicating invalid phone number format or unregistered number | QA Team | 2025-05-23 | Not Start
TC_EP-001_US-001_0003 | US-001 | P | High | Verify login with valid OTP | User has entered a valid phone number and received OTP | 1 | Enter the received OTP in the OTP input field | OTP is displayed as masked characters | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Verify/Submit button | OTP is verified successfully | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | System processes the authentication | User is redirected to the Dashboard/Home screen | QA Team | 2025-05-23 | Not Start
TC_EP-001_US-001_0004 | US-001 | N | High | Verify login with invalid OTP | User has entered a valid phone number and received OTP | 1 | Enter an incorrect OTP in the OTP input field | OTP is displayed as masked characters | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Verify/Submit button | Error message is displayed indicating invalid OTP | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the number of remaining attempts is displayed | Remaining attempts counter is decremented and displayed | QA Team | 2025-05-23 | Not Start
TC_EP-001_US-001_0005 | US-001 | N | Medium | Verify login with expired OTP | User has entered a valid phone number and received OTP, OTP has expired (typically after 5-10 minutes) | 1 | Wait until the OTP expires | OTP expiration timer reaches zero | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Enter the expired OTP in the OTP input field | OTP is displayed as masked characters | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Click on the Verify/Submit button | Error message is displayed indicating expired OTP | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the option to resend OTP is available | Resend OTP button is enabled and clickable | QA Team | 2025-05-23 | Not Start
TC_EP-001_US-001_0006 | US-001 | N | Medium | Verify Login after multiple failed attempts | User has made multiple failed login attempts | 1 | Open the Salary Hero app | App launches successfully and login screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Enter a valid phone number in the phone number field | Phone number is accepted and displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Click on the Continue/Next button | Error message is displayed indicating login attempts | QA Team | 2025-05-23 | Not Start
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test step Result
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test case Result

## TC_US-002
TC No. | US ID | P/N/NE | Priority | Test Case Description | Prerequisite | Ts No | Test steps Description | Expected Result | API Tesing | [5 empty] | Remarks
[9 empty] | Executor | Plan date | Ts Result | TC Result | Test Date | Defect ID
TC_EP-002_US-002_0001 | US-002 | P | High | Verify Dashboard/Home on 1st working day | User is logged in, today is 1st working day | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the earned wage amount is displayed | Earned wage amount is displayed correctly based on 1 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the calculation is correct (daily rate × 1 days) | Calculation is accurate based on the daily rate and 1 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the available balance for withdrawal is displayed | Available balance is displayed and matches the earned wage minus any previous withdrawals | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0002 | US-002 | P | High | Verify view earned wage on 12th working day | User is logged in, today is 12th working day of the month | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the earned wage amount is displayed | Earned wage amount is displayed correctly based on 12 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the calculation is correct (daily rate × 12 days) | Calculation is accurate based on the daily rate and 12 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the available balance for withdrawal is displayed | Available balance is displayed and matches the earned wage minus any previous withdrawals | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0002 | US-002 | P | High | Verify Dashboard/Home on last day of month | User is logged in, today is last day of month | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the earned wage amount is displayed | Earned wage amount is displayed correctly based on 31 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the calculation is correct (daily rate × 31 days) | Calculation is accurate based on the daily rate and 31 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the available balance for withdrawal is displayed | Available balance is displayed and matches the earned wage minus any previous withdrawals | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0002 | US-002 | P | High | Verify Dashboard/Home on last day of month (leap year) | User is logged in, today is last day of month (leap year) | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the earned wage amount is displayed | Earned wage amount is displayed correctly based on 29 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the calculation is correct (daily rate × 29 days) | Calculation is accurate based on the daily rate and 29 working days | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the available balance for withdrawal is displayed | Available balance is displayed and matches the earned wage minus any previous withdrawals | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0005 | US-002 | P | Medium | Verify view earned wage with overtime | User is logged in, has overtime hours recorded | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the earned wage amount includes overtime pay | Earned wage amount includes base pay plus overtime compensation | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the calculation is correct (base pay + overtime pay) | Calculation is accurate based on the base pay and overtime rates | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the available balance for withdrawal reflects the overtime | Available balance includes the overtime compensation | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0006 | US-002 | P | High | Verify view earned wage with previous withdrawals | User is logged in, has made previous withdrawals this month | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the total earned wage amount is displayed | Total earned wage amount is displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify the total withdrawals this pay cycle is displayed | Total withdrawals amount is displayed and matches previous withdrawal transactions | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the available balance for withdrawal is calculated correctly | Available balance equals total earned wage minus total withdrawals | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0007 | US-002 | P | High | Verify Dashboard - mini Transaction History - no Trasaction | User is logged in, new user | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify mini Transaction History | No transaction | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0008 | US-002 | P | High | Verify Dashboard - mini Transaction History - 1 transaction | User is logged in, user has 1 transaction | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify mini Transaction History | display 1 transaction | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0009 | US-002 | P | High | Verify Dashboard - mini Transaction History - 2 transactions | User is logged in, user has 2 transactions | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify mini Transaction History | display 2 transactions | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0010 | US-002 | P | High | Verify Dashboard - mini Transaction History - 3 transactions | User is logged in, user has 3 transactions | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify mini Transaction History | display 3 transactions | QA Team | 2025-05-23 | Not Start
TC_EP-002_US-002_0011 | US-002 | P | High | Verify Dashboard - mini Transaction History - > 3 transactions | User is logged in, user has more than 3 transactions | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify mini Transaction History | display 3 transactions (maximum) with latest | QA Team | 2025-05-23 | Not Start
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test step Result
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test case Result

## TC_US-003
TC No. | US ID | P/N/NE | Priority | Test Case Description | Prerequisite | Ts No | Test steps Description | Expected Result | API Tesing | [5 empty] | Remarks
[9 empty] | Executor | Plan date | Ts Result | TC Result | Test Date | Defect ID
TC_EP-003_US-003_0001 | US-003 | P | High | Verify withdraw full earned wage | User is logged in, has available balance for withdrawal | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed with available balance | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Withdraw button | Withdrawal screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Enter the full available amount in the withdrawal amount field | Full amount is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Click on the Continue/Next button | Withdrawal confirmation screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the withdrawal amount and any applicable fees | Amount and fees are displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Click on the Confirm button | OTP verification screen is displayed | QA Team | 2025-05-23 | Not Start
TC_EP-003_US-003_0002 | US-003 | P | High | Verify withdraw partial earned wage | User is logged in, has available balance for withdrawal | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed with available balance | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Withdraw button | Withdrawal screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Enter a partial amount (less than available balance) in the withdrawal amount field | Partial amount is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Click on the Continue/Next button | Withdrawal confirmation screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the withdrawal amount and any applicable fees | Amount and fees are displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Click on the Confirm button | OTP verification screen is displayed | QA Team | 2025-05-23 | Not Start
TC_EP-003_US-003_0003 | US-003 | N | Medium | Verify withdraw exceeding available amount | User is logged in, has available balance for withdrawal | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed with available balance | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Withdraw button | Withdrawal screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Enter an amount greater than the available balance | Amount is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Click on the Continue/Next button | Error message is displayed indicating the amount exceeds available balance | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the user cannot proceed with the transaction | Continue/Next button remains disabled or error persists until valid amount is entered | QA Team | 2025-05-23 | Not Start
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test step Result
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test case Result

## TC_US-004
TC No. | US ID | P/N/NE | Priority | Test Case Description | Prerequisite | Ts No | Test steps Description | Expected Result | API Tesing | [5 empty] | Remarks
[9 empty] | Executor | Plan date | Ts Result | TC Result | Test Date | Defect ID
TC_EP-003_US-004_0001 | US-004 | P | High | Verify Transaction confirmation with valid OTP | User has initiated withdrawal, received OTP | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed with available balance | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Withdraw button | Withdrawal screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Enter the full available amount in the withdrawal amount field | Full amount is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Click on the Continue/Next button | Withdrawal confirmation screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the withdrawal amount and any applicable fees | Amount and fees are displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Click on the Confirm button | OTP verification screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 7 | Enter valid OTP and confirm | Transaction is processed successfully | QA Team | 2025-05-23 | Not Start
[6 empty] | 8 | Verify the transaction success screen | Success message and transaction details are displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 9 | Verify the updated available balance | Available balance is updated to zero | QA Team | 2025-05-23 | Not Start
TC_EP-003_US-004_0002 | US-004 | P | High | Verify Transaction confirmation with invalid OTP | User has initiated withdrawal, received OTP | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed with available balance | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Withdraw button | Withdrawal screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Enter a partial amount (less than available balance) in the withdrawal amount field | Partial amount is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Click on the Continue/Next button | Withdrawal confirmation screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the withdrawal amount and any applicable fees | Amount and fees are displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Click on the Confirm button | OTP verification screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 7 | Enter valid OTP and confirm | Transaction is processed unsuccessfully | QA Team | 2025-05-23 | Not Start
[6 empty] | 8 | Verify error screen | ??? | QA Team | 2025-05-23 | Not Start
[6 empty] | 9 | Verify the available balance | Available balance does not change | QA Team | 2025-05-23 | Not Start
TC_EP-003_US-004_0003 | US-004 | N | Medium | Verify Transaction confirmation with expired OTP | User has initiated withdrawal, received OTP | 1 | Navigate to the Dashboard/Home screen | Dashboard/Home screen is displayed with available balance | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Withdraw button | Withdrawal screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Enter a partial amount (less than available balance) in the withdrawal amount field | Partial amount is displayed in the input field | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Click on the Continue/Next button | Withdrawal confirmation screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the withdrawal amount and any applicable fees | Amount and fees are displayed correctly | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Click on the Confirm button | OTP verification screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 7 | Enter valid OTP and confirm | Transaction is processed unsuccessfully | QA Team | 2025-05-23 | Not Start
[6 empty] | 8 | Verify error screen | ??? | QA Team | 2025-05-23 | Not Start
[6 empty] | 9 | Verify the available balance | Available balance does not change | QA Team | 2025-05-23 | Not Start
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test step Result
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test case Result

## TC_US-005
TC No. | US ID | P/N/NE | Priority | Test Case Description | Prerequisite | Ts No | Test steps Description | Expected Result | API Tesing | [5 empty] | Remarks
[9 empty] | Executor | Plan date | Ts Result | TC Result | Test Date | Defect ID
TC_EP-004_US-005_0001 | US-004 | P | High | Verify view transaction history - no transaction | User is logged in, no transaction history | 1 | Navigate to the Transaction History screen | Transaction History screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the list of transactions is displayed | no transaction | QA Team | 2025-05-23 | Not Start
TC_EP-004_US-005_0002 | US-004 | P | High | Verify view transaction history - all transactions | User is logged in, has transaction history | 1 | Navigate to the Transaction History screen | Transaction History screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Verify the list of transactions is displayed | List of transactions is displayed in chronological order | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Verify each transaction shows basic information (date, amount, status) | Basic transaction information is displayed for each entry | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the most recent transaction appears at the top | Transactions are sorted with most recent at the top | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify transactions are initially in collapsed view showing basic information | Transactions display basic information in collapsed state | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Click on a transaction to expand it | Transaction expands to show detailed information | QA Team | 2025-05-23 | Not Start
[6 empty] | 7 | Verify the expanded view shows additional details (transaction ID, payment method, etc.) | Expanded view displays all transaction details | QA Team | 2025-05-23 | Not Start
[6 empty] | 8 | Click on the expanded transaction again | Transaction collapses back to basic view | QA Team | 2025-05-23 | Not Start
TC_EP-004_US-005_0003 | US-004 | P | Medium | Verify view transaction history - filter by period: Jan | User is logged in, has transaction history spanning multiple periods | 1 | Navigate to the Transaction History screen | Transaction History screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the period filter option | Period filter options are displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Select a specific period (e.g., This Month, Last Month) | Period filter is applied | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify only transactions from the selected period are displayed | Filtered transactions match the selected period | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Change the period filter to a different period | New period filter is applied | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Verify the transactions update to match the new period | Displayed transactions match the newly selected period | QA Team | 2025-05-23 | Not Start
TC_EP-004_US-005_0004 | US-004 | P | Medium | Verify view transaction history - filter by period: June | User is logged in, has transaction history spanning multiple periods | 1 | Navigate to the Transaction History screen | Transaction History screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the period filter option | Period filter options are displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Select a specific period (e.g., This Month, Last Month) | Period filter is applied | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify only transactions from the selected period are displayed | Filtered transactions match the selected period | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Change the period filter to a different period | New period filter is applied | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Verify the transactions update to match the new period | Displayed transactions match the newly selected period | QA Team | 2025-05-23 | Not Start
TC_EP-004_US-005_0005 | US-004 | P | Medium | Verify view transaction history - filter by period: Dec | User is logged in, has transaction history spanning multiple periods | 1 | Navigate to the Transaction History screen | Transaction History screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the period filter option | Period filter options are displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Select a specific period (e.g., This Month, Last Month) | Period filter is applied | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify only transactions from the selected period are displayed | Filtered transactions match the selected period | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Change the period filter to a different period | New period filter is applied | QA Team | 2025-05-23 | Not Start
[6 empty] | 6 | Verify the transactions update to match the new period | Displayed transactions match the newly selected period | QA Team | 2025-05-23 | Not Start
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test step Result
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test case Result

## TC_US-006
TC No. | US ID | P/N/NE | Priority | Test Case Description | Prerequisite | Ts No | Test steps Description | Expected Result | API Tesing | [5 empty] | Remarks
[9 empty] | Executor | Plan date | Ts Result | TC Result | Test Date | Defect ID
TC_EP-005_US-006_0001 | US-005 | P | Medium | Verify session timeout after inactivity | User is logged in | 1 | Log in to the application | User is successfully logged in and Dashboard is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Leave the application idle for the timeout period (typically 5-15 minutes) | Session timeout period elapses | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Attempt to perform an action after the timeout period | Session timeout message is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the user is redirected to the login screen | Login screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Verify the user needs to authenticate again to access the application | User must enter credentials to log in again | QA Team | 2025-05-23 | Not Start
TC_EP-005_US-006_0002 | US-005 | P | High | Verify manual logout | User is logged in | 1 | Navigate to the profile or settings section | Profile or settings screen is displayed | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Click on the Logout button/option | Logout confirmation dialog is displayed (if applicable) | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Confirm logout (if prompted) | User is logged out successfully | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the user is redirected to the login screen | Login screen is displayed | QA Team | 2025-05-23 | Not Start
[6 empty] | 5 | Attempt to use the back button to access previous screens | User cannot access authenticated screens and remains on login screen | QA Team | 2025-05-23 | Not Start
TC_EP-005_US-006_0003 | US-005 | P | Medium | Verify session persistence across screens | User is logged in | 1 | Navigate through different screens in the application (Dashboard, Transaction History, etc.) | User can navigate between screens without re-authentication | QA Team | 2025-05-23 | Not Start | Not Start
[6 empty] | 2 | Minimize the application and reopen it (within timeout period) | Session is maintained and user remains logged in | QA Team | 2025-05-23 | Not Start
[6 empty] | 3 | Switch to another application and return (within timeout period) | Session is maintained and user remains logged in | QA Team | 2025-05-23 | Not Start
[6 empty] | 4 | Verify the session activity timer resets with user interactions | User remains logged in as long as there is activity within the timeout period | QA Team | 2025-05-23 | Not Start
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test step Result
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test case Result

## Master
Result
Not Start
Pending
Pass
Failed
Not Applicable